Cloud 8 AI Jumpstart — Launch Runbook

Document type: Operational runbook — concise

Owner: Harnoor Minhas / Cloud 8 Data

Date: 2026-04-27

Companion: CLOUD8-ACADEMY-FRAMEWORK-2026-04-27.md

──────────────────────────────────────────────────────────────────────

1. Day 1–7 Launch Plan

Each day has a primary owner and a done-condition. If the done-condition isn't met, do not proceed to the next day's stretch goals.

Day 1 — Monday Apr 28: Infrastructure Day

| Action | Owner | Done When |
| --- | --- | --- |
| Point academy.cloud8data.com subdomain to TITAN /academy route | Harnoor | URL resolves with no error |
| Create Cloud 8 Academy Discord server; set up channels: #announcements #week-1-python #wins #q-and-a #parent-lounge #capstone-lab | Harnoor | Server live, Harnoor is admin |
| Create Replit Team for Education at replit.com/teams/education | Harnoor | Team created, Harnoor is owner |
| Create Hugging Face organization cloud8-academy at huggingface.co | Harnoor | Org page live |
| Create GitHub repo cloud8data/jumpstart-labs (public); commit folder structure: /week01 /week03 /week05 /week07 | Harnoor | Repo live with folders |
| Confirm Stripe webhook is active and posting to TITAN at /api/stripe/webhook | Harnoor | Test event received in TITAN logs |

End of Day 1 hard requirement: academy.cloud8data.com resolves. Discord server is live.

──────────────────────────────────────────────────────────────────────

Day 2 — Tuesday Apr 29: Tile Skeleton

| Action | Owner | Done When |
| --- | --- | --- |
| Build /academy route with 3 tiles: (1) Week 1 intro video tile, (2) Replit fork lab tile, (3) Week 1 reflection assignment tile | FORGE / Harnoor | Tiles render; video plays; lab link opens; assignment form submits |
| Author Week 1 intro video (15 min, unlisted YouTube): "Welcome to Cloud 8 Jumpstart — here's what we're building together" | Harnoor | Video uploaded, unlisted URL recorded |
| Add Week 1 video YouTube ID to video tile | Harnoor | Video embeds in tile |
| Set up /pm roster view with Milana as first entry (Designation: Intern) | FORGE / Harnoor | /pm loads with Milana row |

──────────────────────────────────────────────────────────────────────

Day 3 — Wednesday Apr 30: Lab Content

| Action | Owner | Done When |
| --- | --- | --- |
| Author and push Week 3 Pandas Colab notebook to cloud8data/jumpstart-labs/week03/pandas-intro.ipynb | Harnoor | "Open in Colab" link works; notebook runs cell-by-cell |
| Author and push Week 5 Tokenizers Colab notebook to cloud8data/jumpstart-labs/week05/llm-tokenizers.ipynb | Harnoor | Notebook imports HuggingFace tokenizers, runs without error |
| Author and push Week 7 Decision Tree Colab notebook to cloud8data/jumpstart-labs/week07/sklearn-decision-tree.ipynb | Harnoor | Model trains, accuracy prints |
| Pre-fork Groq chatbot template; confirm it runs with a test API key | Harnoor | Chatbot responds to input |

──────────────────────────────────────────────────────────────────────

Day 4 — Thursday May 1: Enrollment Flow End-to-End Test

| Action | Owner | Done When |
| --- | --- | --- |
| Run full test enrollment: use Stripe test card 4242 4242 4242 4242 for Foundations tier | Harnoor | checkout.session.completed webhook received; test student entry appears in people.json; /academy access granted |
| Test EARLYBIRD50 coupon: verify 50% off applies to first payment only | Harnoor | Stripe invoice shows correct amount |
| Test Resend drip: confirm "Welcome to Cloud 8 Academy" email sends within 2 minutes of enrollment | Harnoor | Email received at test address |
| Author AWS Educate setup guide (1 page): how to create a free account, how to find the Cloud Literacy Badge pathway | Harnoor | Guide saved to cloud8data/jumpstart-labs/setup/aws-educate-setup.md |

──────────────────────────────────────────────────────────────────────

Day 5 — Friday May 2: Dry Run as Student

| Action | Owner | Done When |
| --- | --- | --- |
| Harnoor completes the Week 1 sequence as if he is a student: watch video tile → fork Replit lab → submit Friday update → mark tiles done | Harnoor | All 3 tiles show status "done"; Friday update appears in /pm |
| Note every friction point (confusing UI, broken link, unclear instructions) | Harnoor | Friction log created |
| Fix top 3 friction points identified | FORGE / Harnoor | Fixed and re-tested |
| Send Milana a "you're back from exams — here's your onboarding" email (see Section 3 below) | Harnoor | Email sent |

──────────────────────────────────────────────────────────────────────

Day 6 — Saturday May 3: Content Buffer

| Action | Owner | Done When |
| --- | --- | --- |
| Record Week 2 video (20 min): Variables, Functions, Lists in Python on Replit | Harnoor | Video uploaded unlisted |
| Draft parent welcome email sequence (3 emails — see Section 3) in Resend | Harnoor | All 3 drafts saved, trigger logic set |
| Draft student welcome email sequence (3 emails — see Section 4) in Resend | Harnoor | All 3 drafts saved, trigger logic set |

──────────────────────────────────────────────────────────────────────

Day 7 — Sunday May 4: Pre-Launch Review

| Action | Owner | Done When |
| --- | --- | --- |
| Final checklist: /academy loads ✓, Stripe test enrollment works ✓, Discord server live ✓, 3 Colab notebooks push ✓, email sequences draft ✓ | Harnoor | All boxes checked |
| Set intro class date/time — first paid intro class: Monday May 12, 7:00 PM Eastern | Harnoor | Calendly event created; Zoom link generated |
| Milana onboarded: /pm access, Discord admin, Calendly integration, outreach starting Monday | Milana + Harnoor | Milana confirms she can see /pm, is Discord admin, has Calendly access |

──────────────────────────────────────────────────────────────────────

2. First-3-Students Dry Run Script

Run this May 5–9 with 3 real students (family, friends, or known parents). These are not paid — scholarship or comp seats. Purpose: stress-test the UX before charging money.

Recruiting the 3

Harnoor sends personal texts to 3 parents he already knows: "I'm building something for high school students. I'd like your kid to be one of the first 3 to try it — free, 2 hours total. I want honest feedback. Can [student name] join me next Tuesday evening?"

Conversion rate expected: 2 out of 3 yes. Aim for 3 contacts to get 3 confirmations.

The Dry Run Session (60 min, May 6, 7 PM)

[technical detail omitted from printable edition — see source repository for the code block]

Post Dry Run (May 7–8)

Review the 3 feedback forms. Identify the top 3 friction points. Fix them before May 12 intro class. Write a 5-line summary in /pm Friday update: "dry run findings: [X, Y, Z]. Fixed: [A, B]. Still open: [C]."

──────────────────────────────────────────────────────────────────────

3. Parent Email Sequence (3 Emails)

Trigger: parent attends intro class and downloads Parent Packet (or provides email at class sign-in).

Sender: harnoor@cloud8data.com

Platform: Resend, with 24h / 72h / 7-day delays.

──────────────────────────────────────────────────────────────────────

Email 1 — Sent within 60 minutes of class end

Subject: Your child just saw what's possible — here's the next step

Hi [Parent First Name],

Thank you for joining tonight's Cloud 8 AI Jumpstart intro class. Your child's attention for the full 75 minutes tells me something: they want this.

I want to make the next step easy for you. Attached is the Parent Packet — everything about the program, pricing, safety standards, and refund policy.

The 50% early-bird offer (any tier, first month only) expires exactly 24 hours from now.

If you have questions, book a 15-minute call with me directly: [Calendly link]

Or enroll at: cloud8data.com/jumpstart

— Harnoor

P.S. Your child is 1 of 20 spots. Cohort 2 doesn't open until September at full pricing.

──────────────────────────────────────────────────────────────────────

Email 2 — Sent 72 hours after class

Subject: A question I get from every parent

Hi [Parent First Name],

The most common thing parents tell me after the intro class: "My child loved it — but I want to understand what they'll actually walk away with."

Fair. Here's the concrete answer:

After 16 weeks, your child will have:

A working AI app, publicly hosted, with a shareable URL

A GitHub portfolio with every project they built

A Certificate of Completion from Cloud 8 Data (AWS Partner company), signed by me personally

19 years of my professional network, not a chatbot's advice

That's what changes the college application. Not the grade. Not the test score. A URL that points to something real they built.

Enrollment is open: cloud8data.com/jumpstart

If the early-bird window passed, reply to this email — I'll see what I can do.

— Harnoor

──────────────────────────────────────────────────────────────────────

Email 3 — Sent 7 days after class

Subject: Last thing I'll send you

Hi [Parent First Name],

I've sent you a couple of emails about Cloud 8 AI Jumpstart. This is the last one.

Cohort 1 has [X] of 20 seats filled. We start May 20.

If your child wants in, enrollment closes May 18.

Three things I want you to know before you decide:

7-day full refund. If your child tries Week 1 and it isn't the right fit, you get every dollar back. No questions asked.

3 hours per week. That's it. Around sports, homework, and everything else.

I'll vouch for your child. Not a course completion email. A real letter of recommendation from a professional with 19 years of Fortune 500 experience, addressed to the specific university they're targeting (Tier 3 only).

If now is not the right time, I understand. I'll run Cohort 2 in September.

cloud8data.com/jumpstart

— Harnoor

──────────────────────────────────────────────────────────────────────

4. Student Email Sequence (3 Emails)

Trigger: student enrollment confirmed (Stripe checkout.session.completed webhook).

Sender: harnoor@cloud8data.com

Platform: Resend.

──────────────────────────────────────────────────────────────────────

Email 1 — Sent immediately on enrollment

Subject: You're in. Welcome to Cloud 8 Academy.

Hey [Student First Name],

You just enrolled in Cloud 8 AI Jumpstart, Cohort 1. That took guts — most people watch the intro class and wait. You didn't.

Here's what happens next:

Your academy is live at: academy.cloud8data.com (log in with this email)

Join the Discord server: [Discord invite link] — say hi in #wins

Week 1 starts [date] — your first live class is [date + time]

This week, before our first class, do one thing: open your academy page and watch the Week 1 intro video. It's 15 minutes. That's your only homework.

Any questions? Reply to this email. I read every reply.

— Harnoor

──────────────────────────────────────────────────────────────────────

Email 2 — Sent 48 hours after enrollment

Subject: Your setup checklist for Week 1

Hey [Student First Name],

Week 1 is coming up fast. Here's your 3-step setup so you're not scrambling the night of:

Step 1 — Create your Replit account (3 min)

Go to replit.com and sign up with a free account. No credit card needed. This is where you'll write your first Python.

Step 2 — Create your GitHub account (3 min)

Go to github.com and sign up. Apply for the GitHub Student Developer Pack at education.github.com — it's free and gives you Codespaces (cloud coding environment) for the capstone.

Step 3 — Join Discord and say hi (2 min)

If you haven't already, join the Cloud 8 Academy server: [Discord link]. Post your name and grade in #wins.

That's it. See you at the first class.

— Harnoor

──────────────────────────────────────────────────────────────────────

Email 3 — Sent 24 hours before first live class

Subject: Tomorrow night — what to have ready

Hey [Student First Name],

Your first Cloud 8 live class is tomorrow at [time] Eastern.

Here's what to have open:

Zoom: [Zoom link] — join 5 minutes early

Replit: replit.com (logged in)

Groq console: console.groq.com — create a free account before class so you have your API key ready

This email: so you can paste the template fork URL when I share it

We will build a real AI chatbot in 35 minutes. Together. You will run it yourself.

See you tomorrow.

— Harnoor

P.S. If you have a question before class, reply here. I'll answer.

──────────────────────────────────────────────────────────────────────

5. Demo Class Agenda (60 Minutes)

This is the first live class for enrolled students — distinct from the intro/sales class in live-demo-script.md.

[technical detail omitted from printable edition — see source repository for the code block]

──────────────────────────────────────────────────────────────────────

6. First Lab: Replit Chatbot Starter

Template URL: https://replit.com/@replit-matt/Chat-with-Groq?v=1#main.py

Groq API (free): https://console.groq.com

Model used: Meta Llama-3 via Groq API (fast, free tier, no credit card)

What students need:

A Replit free account (replit.com)

A Groq free account (console.groq.com) — instant API key, no card

20 minutes

Fork and run steps:

Click the template URL above

Click "Fork" (top right)

In your forked Repl, click "Secrets" (padlock icon in left sidebar)

Add secret: Key = GROQ_API_KEY, Value = [your key from console.groq.com]

Click "Run"

Type a message in the chat interface that appears

Customizing the system prompt (core exercise):

Open main.py. Find this line:

[technical detail omitted from printable edition — see source repository for the code block]

Change it to something specific:

[technical detail omitted from printable edition — see source repository for the code block]

Run again. Test it. Try to break it. That's the Balance AI+Brain moment.

Backup Replit chatbot (no API key needed, for demo fallback):

Harnoor can pre-build a hosted Repl with his own API key, deployed as a public web app. Share the URL; students interact without needing any account setup. Use this as a live demo backup if student signups fail during class.

──────────────────────────────────────────────────────────────────────

Runbook last updated 2026-04-27. Owner: Harnoor Minhas. Use with: CLOUD8-ACADEMY-FRAMEWORK-2026-04-27.md